## Roadmap Data
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Preproject
| Total time: | 21
| Time left: | 0
| Time spent: | 21
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number)
| Completed | Create github repo for: -website -mobile -docs | 1 - High |  | 1 | 34
| Completed | Create sharepoint | 1 - High |  | 1 | 34
| Completed | Create roadmap | 2 - Med |  | 1 | 34
| Completed | Create repport template | 1 - High |  | 1 | 34
| Completed | Get school NDA completed | 1 - High | færdiggørelse udskudt til launchphase | 1 | 34
| Completed | Item order | 1 - High | udskudt til launchphase | 1 | 34
| Completed | Development plan (Preproject) | 1 - High |  | 1 | 34
| Completed | Rich picture | 1 - High |  | 1 | 34
| Completed | Story telling | 1 - High |  | 1 | 34
| Completed | Prelim. Use cases | 1 - High |  | 1 | 34
| Completed | Stakeholder analysis | 1 - High |  | 1 | 34
| Completed | System definition | 1 - High |  | 1 | 34
| Completed | Development plan (Launch phase) | 1 - High |  | 1 | 34
| Completed | Quote | 1 - High |  | 1 | 34
| Completed | Meeting agenda | 1 - High |  | 1 | 34
| Completed | Problem describsion | 2 - Med | færdiggørelse udskudt til launchphase | 4 | 35
| Completed | finish preproject report | 1 - High |  | 1 | 35
| Completed | Book mew meetings | 2 - Med |  | 1 | 35
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet. | Add new items by inserting new rows above this line

## Agile Roadmap
An Agile Roadmap displaying milestones and activities from Raodmap Data worksheet is in this worksheet. Title is in cell B1. Results that have the phrase "No Change" are highlighted light orange, rgb(255, 230, 210). Completed milestones or activities are highlighted light green, rgb(237,251,219). | Preproject Roadmap
Chart headings are in cells B2, D2, F2, and H2. They read: Completed, Current, Near Term, and Future. Modify these headings to change the Target selection values in the Roadmap Data table in the Roadmap Data worksheet. Cells B3 through H20 contain the Milestones and activities for the headings in this row. Milestones and activities are created in the Roadmap Data worksheet. Do NOT modify or delete entries in this worksheet. Update the Roadmap Data table in the Roadmap Data worksheet to update content in this worksheet. This is the last instruction in this worksheet. | Completed | Current | Near Term | Future
Create github repo for: -website -mobile -docs
Create sharepoint
Create roadmap
Create repport template
Get school NDA completed færdiggørelse udskudt til launchphase
Item order udskudt til launchphase
Development plan (Preproject)
Rich picture
Story telling
Prelim. Use cases
Stakeholder analysis
System definition
Development plan (Launch phase)
Quote
Meeting agenda
Problem describsion færdiggørelse udskudt til launchphase
finish preproject report
Book mew meetings

## About
About this workbook
Guide for screen readers
There are 3 worksheets in this workbook. Roadmap Data Agile Roadmap About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. Hidden text will not print. To remove these instructions from any worksheet, simply delete column A.
About this Workbook
Enter milestone information in the Roadmap Data worksheet. Be sure to sort by priority followed by milestone to capture the Completed, Current, Near Term, and Future view in decreasing priority--with highest priority items listed at the top. The Roadmap in the Agile Roadmap worksheet is auto updated.
This is the last instruction in this worksheet.