## Roadmap Data
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Launch Phase roadmap
| Total time: | 59
| Time left: | 0
| Time spent: | 59
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer
| Completed | Requirement analysis | 1 - High | reviewed | 5 | 37
| Completed | Problem domain analysis | 1 - High | reviewed | 1 | 37
| Completed | Usage domain analysis | 1 - High | reviewed | 9 | 37
| Completed | Interface anlysis | 1 - High | reviewed | 11 | 37
| Completed | Functionality Analysis | 1 - High | reviewed | 3 | 37
| Completed | System behaviour analysis | 1 - High | reviewed | 1 | 37
| Completed | Design constraint analysis | 1 - High | reviewed | 2 | 37
| Completed | System architecture Design - app | 1 - High | reviewed | 1 | 37
| Completed | System architecture Design - embed | 1 - High | reviewed | 1 | 37
| Completed | System architecture Design - database | 1 - High | reviewed | 1 | 37
| Completed | System architecture Design - website | 1 - High | reviewed | 1 | 37
| Completed | System architecture Design - rapport | 1 - High | reviewed | 1 | 37
| Completed | Selecting technical platform | 1 - High | reviewed | 2 | 37
| Completed | Development plan (Realization phase) | 1 - High | reviewed | 4 | 37
| Completed | Quotation (preproject) | 1 - High | reviewed | 2 | 37
| Completed | Product acceptance | 1 - High | reviewed | 4 | 37
| Completed | rydde op i "sprint deliverable" | 1 - High | reviewed | 1 | 37
| Completed | Samle endelige launch rapport | 1 - High | reviewed | 3 | 37
| Completed | problem formulering | 1 - High | reviewed | 3 | 37
| Completed | lave dagsorden til abus/eurowind møde | 1 - High | reviewed | 1 | 36 tirsdag
| Completed | lave genkaldende møde til anders | 1 - High | reviewed | 1
| Completed | Sende endelige launch rapport til EWE | 1 - High | reviewed | 1
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet. | Add new items by inserting new rows above this line

## Agile Roadmap
An Agile Roadmap displaying milestones and activities from Raodmap Data worksheet is in this worksheet. Title is in cell B1. Results that have the phrase "No Change" are highlighted light orange, rgb(255, 230, 210). Completed milestones or activities are highlighted light green, rgb(237,251,219). | Launch phase Roadmap
Chart headings are in cells B2, D2, F2, and H2. They read: Completed, Current, Near Term, and Future. Modify these headings to change the Target selection values in the Roadmap Data table in the Roadmap Data worksheet. Cells B3 through H20 contain the Milestones and activities for the headings in this row. Milestones and activities are created in the Roadmap Data worksheet. Do NOT modify or delete entries in this worksheet. Update the Roadmap Data table in the Roadmap Data worksheet to update content in this worksheet. This is the last instruction in this worksheet. | Completed | Current | Temp finished | Future
Requirement analysis reviewed
Problem domain analysis reviewed
Usage domain analysis reviewed
Interface anlysis reviewed
Functionality Analysis reviewed
System behaviour analysis reviewed
Design constraint analysis reviewed
System architecture Design - app reviewed
System architecture Design - embed reviewed
System architecture Design - database reviewed
System architecture Design - website reviewed
System architecture Design - rapport reviewed
Selecting technical platform reviewed
Development plan (Realization phase) reviewed
Quotation (preproject) reviewed
Product acceptance reviewed
rydde op i "sprint deliverable" reviewed
Samle endelige launch rapport reviewed
problem formulering reviewed
lave dagsorden til abus/eurowind møde reviewed
lave genkaldende møde til anders reviewed
Sende endelige launch rapport til EWE reviewed

## About
About this workbook
Guide for screen readers
There are 3 worksheets in this workbook. Roadmap Data Agile Roadmap About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. Hidden text will not print. To remove these instructions from any worksheet, simply delete column A.
About this Workbook
Enter milestone information in the Roadmap Data worksheet. Be sure to sort by priority followed by milestone to capture the Completed, Current, Near Term, and Future view in decreasing priority--with highest priority items listed at the top. The Roadmap in the Agile Roadmap worksheet is auto updated.
This is the last instruction in this worksheet.