## Data website+database
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Website + database roadmap
| Total time: | 69.5 | days: | 9.9286
| Time left: | 64.5
| Time spent: | 5
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer | krav | LP = landing page DMP = database manipulation page BF = background functions LPF = landing page + filter RAPI: Rest API
| Future | Filtre: personal info | 1 - High |  | 2.5 | 39 |  | WEB-4, WEB-8
| Future | Filtre: personal fac. info | 1 - High |  | 2.5 | 39 |  | WEB-4, WEB-8
| Future | Filtre: User logs | 1 - High |  | 2.5 | 39 |  | WEB-9, WEB-10
| Future | Filtre: Fac. Logs | 1 - High |  | 2.5 | 39 |  | WEB-9, WEB-10
| Future | Login | 1 - High |  | 4 | 38 |  | WEB-3
| Future | LP: Office user dahboard | 1 - High |  | 1 | 38 |  | WEB-4
| Future | LP: Field user dashboard | 1 - High |  | 1 | 38 |  | WEB-4
| Future | LP: Edit fac. Lp | 1 - High |  | 1 | 38 |  | WEB-17
| Future | LP: Add/edit/remove fac. Lp | 1 - High |  | 1 | 38 |  | WEB-16, WEB-17, WEB-18
| Future | DMP: Create user | 1 - High |  | 2.5 | 38 |  | WEB-1, WEB-3, WEB-15
| Future | DMP: Edit user | 1 - High |  | 2.5 | 38 |  | WEB-2, WEB-4
| Future | DMP: Give fac. Access | 1 - High |  | 2.5 | 38 |  | WEB-4, WEB-6, WEB-7
| Future | DMP: Remove fac. Access | 1 - High |  | 2.5 | 38 |  | WEB-4, WEB-5
| Future | DMP: Add fac. | 1 - High |  | 2.5 | 38 |  | WEB-16
| Future | DMP: Remove fac. | 1 - High |  | 2.5 | 38 |  | WEB-18
| Future | DMP: Edit fac. | 1 - High |  | 2.5 | 38 |  | WEB-17
| Future | BF: CU code gen. | 1 - High |  | 4 | 39 |  | WEB-1, WEB-15
| Future | LPF: Edit user lp | 1 - High |  | 4 | 39 |  | WEB-2, WEB-4
| Future | Template: strukturer database | 1 - High |  | 5 | 37 |  | WEB-1, WEB-2, WEB-3, WEB-4, WEB-5, WEB-6, WEB-7, WEB-8, WEB-9, WEB-10, WEB-11, WEB-13
| Future | Settings: django | 1 - High |  | 1 | 38 |  | Alle WEB
| Completed | AWS | 1 - High | reviewed | 5 | 37 |  | None
| Future | RAPI: Authorisation | 1 - High |  | 5 | 39 |  | WEB-13
| Future | RAPI: Fetch data | 1 - High |  | 5 | 39 |  | WEB-13
| Future | RAPI: Insert data | 1 - High |  | 5 | 39 |  | WEB-13
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet. | Add new items by inserting new rows above this line
NTH
| Future | bootstrap 4 | 3 - Low |  | 40

## Roadmap Website+database
An Agile Roadmap displaying milestones and activities from Raodmap Data worksheet is in this worksheet. Title is in cell B1. Results that have the phrase "No Change" are highlighted light orange, rgb(255, 230, 210). Completed milestones or activities are highlighted light green, rgb(237,251,219). | Launch phase Roadmap
Chart headings are in cells B2, D2, F2, and H2. They read: Completed, Current, Near Term, and Future. Modify these headings to change the Target selection values in the Roadmap Data table in the Roadmap Data worksheet. Cells B3 through H20 contain the Milestones and activities for the headings in this row. Milestones and activities are created in the Roadmap Data worksheet. Do NOT modify or delete entries in this worksheet. Update the Roadmap Data table in the Roadmap Data worksheet to update content in this worksheet. This is the last instruction in this worksheet. | Completed | Current | Temp finished | Future
| AWS reviewed |  |  | Filtre: personal info
Filtre: personal fac. info
Filtre: User logs
Filtre: Fac. Logs
Login
LP: Office user dahboard
LP: Field user dashboard
LP: Edit fac. Lp
LP: Add/edit/remove fac. Lp
DMP: Create user
DMP: Edit user
DMP: Give fac. Access
DMP: Remove fac. Access
DMP: Add fac.
DMP: Remove fac.
DMP: Edit fac.
BF: CU code gen.
LPF: Edit user lp
Template: strukturer database
Settings: django
RAPI: Authorisation
RAPI: Fetch data
RAPI: Insert data

## Data mobile app
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Mobil app roadmap
| Total time: | 180 | days: | 25.7143
| Time left: | 180
| Time spent: | 0 | [6 empty] | Tids estimering er umiddelbart sat højt.
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer | krav
| Future | View: Login | 1 - High |  | 4 | 41 |  | APP-2, APP-3
| Future | View: Fingerprint scan | 1 - High |  | 4 | 41 |  | APP-3
| Future | View: User dashboard | 1 - High |  | 4 | 41 |  | APP-10
| Future | View: Find facilities | 1 - High |  | 4 | 41 |  | APP-5
| Future | View:Facility status notice | 1 - High |  | 4 | 41 |  | APP-10
| Future | Function: Login | 1 - High |  | 12 | 42 |  | APP-2, APP-3
| Future | Function: Open "create user" web page | 1 - High |  | 8 | 42 |  | APP-1
| Future | Function: Fingerprint scan | 1 - High |  | 24 | 42 |  | APP-3
| Future | Function: Unlock facilities | 1 - High |  | 12 | 43 |  | APP-4, APP-6, APP-7, APP-8
| Future | Function: Rest API | 1 - High |  | 24 | 43 |  | APP-6, APP-7, APP-8
| Future | Function: Find facilities | 1 - High |  | 24 | 44 |  | APP-5
| Future | Function: Connect to facilities | 1 - High |  | 24 | 44 |  | APP-5, APP-8
| Future | Redirect: Find facilities | 1 - High |  | 2 | 44 |  | APP-5
|  | Research |  |  | 10 | 41 |  | None
|  | Research |  |  | 10 | 40 |  | None
|  | Research |  |  | 10 | 39 |  | None
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet. | Add new items by inserting new rows above this line

## Roadmap mobile app
An Agile Roadmap displaying milestones and activities from Raodmap Data worksheet is in this worksheet. Title is in cell B1. Results that have the phrase "No Change" are highlighted light orange, rgb(255, 230, 210). Completed milestones or activities are highlighted light green, rgb(237,251,219). | Launch phase Roadmap
Chart headings are in cells B2, D2, F2, and H2. They read: Completed, Current, Near Term, and Future. Modify these headings to change the Target selection values in the Roadmap Data table in the Roadmap Data worksheet. Cells B3 through H20 contain the Milestones and activities for the headings in this row. Milestones and activities are created in the Roadmap Data worksheet. Do NOT modify or delete entries in this worksheet. Update the Roadmap Data table in the Roadmap Data worksheet to update content in this worksheet. This is the last instruction in this worksheet. | Completed | Current | Temp finished | Future
View: Login
View: Fingerprint scan
View: User dashboard
View: Find facilities
View:Facility status notice
Function: Login
Function: Open "create user" web page
Function: Fingerprint scan
Function: Unlock facilities
Function: Rest API
Function: Find facilities
Function: Connect to facilities
Redirect: Find facilities

## Data embed + lock
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Embed + lock roadmap
| Total time: | 43 | days: | 6.1429
| Time left: | 43
| Time spent: | 0
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer | krav
| Future | Function: Bluetooth communication |  |  | 24 | 40 |  | EMB-1
| Future | Function: Verify key |  |  | 6 | 40 |  | EMB-3, EMB-4
| Future | Function: Lock controller |  |  | 6 | 40 |  | EMB-2, EMB-5
| Future | Build: Lock and embed circuit |  |  | 6 | 40 |  | EMB-2, EMB-5
| Future | Buy: Hardware and components |  |  | 1 | 40 |  | None
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet. | Add new items by inserting new rows above this line

## Roadmap embed + lock
An Agile Roadmap displaying milestones and activities from Raodmap Data worksheet is in this worksheet. Title is in cell B1. Results that have the phrase "No Change" are highlighted light orange, rgb(255, 230, 210). Completed milestones or activities are highlighted light green, rgb(237,251,219). | Launch phase Roadmap
Chart headings are in cells B2, D2, F2, and H2. They read: Completed, Current, Near Term, and Future. Modify these headings to change the Target selection values in the Roadmap Data table in the Roadmap Data worksheet. Cells B3 through H20 contain the Milestones and activities for the headings in this row. Milestones and activities are created in the Roadmap Data worksheet. Do NOT modify or delete entries in this worksheet. Update the Roadmap Data table in the Roadmap Data worksheet to update content in this worksheet. This is the last instruction in this worksheet. | Completed | Current | Temp finished | Future
Function: Bluetooth communication
Function: Verify key
Function: Lock controller
Build: Lock and embed circuit
Buy: Hardware and components

## Total data
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Website + database roadmap
| Total time: | 292.5 | days: | 41.7857
| Time left: | 287.5
| Time spent: | 5
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer | krav | område | LP = landing page DMP = database manupulation page BF = background functions LPF = landing page + filter
| Future | Filtre: personal info | 1 - High |  | 2.5 | 39 |  | WEB-4, WEB-8 | Website
| Future | Filtre: personal fac. info | 1 - High |  | 2.5 | 39 |  | WEB-4, WEB-8 | Website
| Future | Filtre: User logs | 1 - High |  | 2.5 | 39 |  | WEB-9, WEB-10 | Website
| Future | Filtre: Fac. Logs | 1 - High |  | 2.5 | 39 |  | WEB-9, WEB-10 | Website
| Future | Login | 1 - High |  | 4 | 38 |  | WEB-3 | Website
| Future | LP: Office user dahboard | 1 - High |  | 1 | 38 |  | WEB-4 | Website
| Future | LP: Field user dashboard | 1 - High |  | 1 | 38 |  | WEB-4 | Website
| Future | LP: Edit fac. Lp | 1 - High |  | 1 | 38 |  | WEB-17 | Website
| Future | LP: Add/edit/remove fac. Lp | 1 - High |  | 1 | 38 |  | WEB-16, WEB-17, WEB-18 | Website
| Future | DMP: Create user | 1 - High |  | 2.5 | 38 |  | WEB-1, WEB-3, WEB-15 | Website
| Future | DMP: Edit user | 1 - High |  | 2.5 | 38 |  | WEB-2, WEB-4 | Website
| Future | DMP: Give fac. Access | 1 - High |  | 2.5 | 38 |  | WEB-4, WEB-6, WEB-7 | Website
| Future | DMP: Remove fac. Access | 1 - High |  | 2.5 | 38 |  | WEB-4, WEB-5 | Website
| Future | DMP: Add fac. | 1 - High |  | 2.5 | 38 |  | WEB-16 | Website
| Future | DMP: Remove fac. | 1 - High |  | 2.5 | 38 |  | WEB-18 | Website
| Future | DMP: Edit fac. | 1 - High |  | 2.5 | 38 |  | WEB-17 | Website
| Future | BF: CU code gen. | 1 - High |  | 4 | 39 |  | WEB-1, WEB-15 | Website
| Future | LPF: Edit user lp | 1 - High |  | 4 | 39 |  | WEB-2, WEB-4 | Website
| Future | Template: strukturer database | 1 - High |  | 5 | 37 |  | WEB-1, WEB-2, WEB-3, WEB-4, WEB-5, WEB-6, WEB-7, WEB-8, WEB-9, WEB-10, WEB-11, WEB-13 | Website
| Future | Settings: django | 1 - High |  | 1 | 38 |  | Alle WEB | Website
| Completed | AWS | 1 - High | reviewed | 5 | 37 |  | None | Website
| Future | RAPI: Authorisation | 1 - High |  | 5 | 39 |  | WEB-13 | Website
| Future | RAPI: Fetch data | 1 - High |  | 5 | 39 |  | WEB-13 | Website
| Future | RAPI: Insert data | 1 - High |  | 5 | 39 |  | WEB-13 | Website
| Future | View: Login | 1 - High |  | 4 | 41 |  | APP-2, APP-3 | App
| Future | View: Fingerprint scan | 1 - High |  | 4 | 41 |  | APP-3 | App
| Future | View: User dashboard | 1 - High |  | 4 | 41 |  | APP-10 | App
| Future | View: Find facilities | 1 - High |  | 4 | 41 |  | APP-5 | App
| Future | View:Facility status notice | 1 - High |  | 4 | 41 |  | APP-10 | App
| Future | Function: Login | 1 - High |  | 12 | 42 |  | APP-2, APP-3 | App
| Future | Function: Open "create user" web page | 1 - High |  | 8 | 42 |  | APP-1 | App
| Future | Function: Fingerprint scan | 1 - High |  | 24 | 42 |  | APP-3 | App
| Future | Function: Unlock facilities | 1 - High |  | 12 | 43 |  | APP-4, APP-6, APP-7, APP-8 | App
| Future | Function: Rest API | 1 - High |  | 24 | 43 |  | APP-6, APP-7, APP-8 | App
| Future | Function: Find facilities | 1 - High |  | 24 | 44 |  | APP-5 | App
| Future | Function: Connect to facilities | 1 - High |  | 24 | 44 |  | APP-5, APP-8 | App
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet. | Future | Redirect: Find facilities | 1 - High |  | 2 | 44 |  | APP-5 | App
|  | Research |  |  | 10 | 41 |  | None | App
|  | Research |  |  | 10 | 40 |  | None | App
|  | Research |  |  | 10 | 39 |  | None | App
| Future | Function: Bluetooth communication |  |  | 24 | 40 |  | EMB-1 | Embed
| Future | Function: Verify key |  |  | 6 | 40 |  | EMB-3, EMB-4 | Embed
| Future | Function: Lock controller |  |  | 6 | 40 |  | EMB-2, EMB-5 | Embed
| Future | Build: Lock and embed circuit |  |  | 6 | 40 |  | EMB-2, EMB-5 | Embed
| Future | Buy: Hardware and components |  |  | 1 | 40 |  | None | Embed
Add new items by inserting new rows above this line
NTH
| Future | bootstrap 4 | 3 - Low |  | 40

## Total Roadmap
Website: |  |  | timer: | 292.5 |  | project completion rate: | 2.381%
App: |  |  | dage: | 41.7857
Embed: |  |  | uger: | 4.1786
| Development | [7 empty] | Test |  |  | Report
Uge | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Timer i alt | 10 | 26.5 | 43 | 53 | 30 | 44 | 36 | 50 | 0 | 0 | 0 | 0 | 0 | 0
Opg. 1 | [Website] Opg: Template: strukturer database Krav: WEB-1, WEB-2, WEB-3, WEB-4, WEB-5, WEB-6, WEB-7, WEB-8, WEB-9, WEB-10, WEB-11, WEB-13 | [Website] Opg: Login Krav: WEB-3 | [Website] Opg: Filtre: personal info Krav: WEB-4, WEB-8 | [App] Opg: Research Krav: None | [App] Opg: View: Login Krav: APP-2, APP-3 | [App] Opg: Function: Login Krav: APP-2, APP-3 | [App] Opg: Function: Unlock facilities Krav: APP-4, APP-6, APP-7, APP-8 | [App] Opg: Function: Find facilities Krav: APP-5
Opg. 2 | [Website] Opg: AWS Krav: None | [Website] Opg: LP: Office user dahboard Krav: WEB-4 | [Website] Opg: Filtre: personal fac. info Krav: WEB-4, WEB-8 | [Embed] Opg: Function: Bluetooth communication Krav: EMB-1 | [App] Opg: View: Fingerprint scan Krav: APP-3 | [App] Opg: Function: Open "create user" web page Krav: APP-1 | [App] Opg: Function: Rest API Krav: APP-6, APP-7, APP-8 | [App] Opg: Function: Connect to facilities Krav: APP-5, APP-8
Opg. 3 |  | [Website] Opg: LP: Field user dashboard Krav: WEB-4 | [Website] Opg: Filtre: User logs Krav: WEB-9, WEB-10 | [Embed] Opg: Function: Verify key Krav: EMB-3, EMB-4 | [App] Opg: View: User dashboard Krav: APP-10 | [App] Opg: Function: Fingerprint scan Krav: APP-3 |  | [App] Opg: Redirect: Find facilities Krav: APP-5
Opg. 4 |  | [Website] Opg: LP: Edit fac. Lp Krav: WEB-17 | [Website] Opg: Filtre: Fac. Logs Krav: WEB-9, WEB-10 | [Embed] Opg: Function: Lock controller Krav: EMB-2, EMB-5 | [App] Opg: View: Find facilities Krav: APP-5
Opg. 5 |  | [Website] Opg: LP: Add/edit/remove fac. Lp Krav: WEB-16, WEB-17, WEB-18 | [Website] Opg: BF: CU code gen. Krav: WEB-1, WEB-15 | [Embed] Opg: Build: Lock and embed circuit Krav: EMB-2, EMB-5 | [App] Opg: View:Facility status notice Krav: APP-10
Opg. 6 |  | [Website] Opg: DMP: Create user Krav: WEB-1, WEB-3, WEB-15 | [Website] Opg: LPF: Edit user lp Krav: WEB-2, WEB-4 | [Embed] Opg: Buy: Hardware and components Krav: None | [App] Opg: Research Krav: None
Opg. 7 |  | [Website] Opg: DMP: Edit user Krav: WEB-2, WEB-4 | [Website] Opg: RAPI: Authorisation Krav: WEB-13
Opg. 8 |  | [Website] Opg: DMP: Give fac. Access Krav: WEB-4, WEB-6, WEB-7 | [Website] Opg: RAPI: Fetch data Krav: WEB-13
Opg. 9 |  | [Website] Opg: DMP: Remove fac. Access Krav: WEB-4, WEB-5 | [Website] Opg: RAPI: Insert data Krav: WEB-13
Opg. 10 |  | [Website] Opg: DMP: Add fac. Krav: WEB-16 | [App] Opg: Research Krav: None
Opg. 11 |  | [Website] Opg: DMP: Remove fac. Krav: WEB-18
Opg. 12 |  | [Website] Opg: DMP: Edit fac. Krav: WEB-17
Opg. 13 |  | [Website] Opg: Settings: django Krav: Alle WEB
Opg. 14
Opg. 15
Opg. 16
Opg. 17
Opg. 18
Opg. 19
Opg. 20
Opg. 21
Opg. 22
Opg. 23