## Data website+database
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Website + database roadmap
| Total time: | 199 | days: | 28.4286
| Time left: | 0
| Time spent: | 199
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer | krav | LP = landing page DMP = database manipulation page BF = background functions LPF = landing page + filter RAPI: Rest API
| Completed | Filtre: personal info | 1 - High | Reviewed | 5 | 39 |  | WEB-4, WEB-8
| Completed | Filtre: personal fac. info | 1 - High | Reviewed | 5 | 39 |  | WEB-4, WEB-8
| Completed | Filtre: User logs | 1 - High | Reviewed | 6 | 40 |  | WEB-9, WEB-10
| Completed | Filtre: Fac. Logs | 1 - High | Reviewed | 1 | 40 |  | WEB-9, WEB-10
| Completed | admin bruger | 1 - High | Reviewed | 10 | 38 |  | WEB-2, WEB-11
| Completed | csrf token inserts on all pages | 1 - High | Reviewed | 1 | 39
| Completed | Usertype control | 1 - High | Reviewed | 1 | 39 | only field user can access field user page etc.
| Completed | Login | 1 - High | Reviewed | 10 | 38 |  | WEB-3
| Completed | LP: Office user dahboard | 1 - High | Reviewed | 6 | 38 |  | WEB-4
| Completed | LP: Field user dashboard | 1 - High | Reviewed | 4 | 38 |  | WEB-4
| Completed | LP: Edit fac. Lp | 1 - High | Reviewed | 4 | 38 |  | WEB-17
| Completed | LP: Add/edit/remove fac. Lp | 1 - High | Reviewed | 4 | 38 |  | WEB-16, WEB-17, WEB-18
| Completed | DMP: Create user | 1 - High | Reviewed | 2.5 | 39 |  | WEB-1, WEB-3, WEB-15
| Completed | DMP: Edit other user | 1 - High | Reviewed | 4 | 39 |  | WEB-2, WEB-4
| Completed | DMP: Give fac. Access | 1 - High | Reviewed | 8 | 40 |  | WEB-4, WEB-6, WEB-7
| Completed | DMP: Remove fac. Access | 1 - High | Reviewed | 8 | 40 |  | WEB-4, WEB-5
| Completed | DMP: Add fac. | 1 - High | Reviewed | 2.5 | 39 |  | WEB-16
| Completed | DMP: Remove fac. | 1 - High | Reviewed | 2.5 | 39 |  | WEB-18
| Completed | DMP: Edit fac. | 1 - High | Reviewed | 2.5 | 39 |  | WEB-17
| Completed | BF: CU code gen. | 1 - High | Reviewed | 4 | 39 |  | WEB-1, WEB-15
| Completed | LPF: Edit user lp | 1 - High | Reviewed | 4 | 39 |  | WEB-2, WEB-4
| Completed | Template: strukturer database + implementation | 1 - High | Reviewed | 10 | 38 |  | WEB-1, WEB-2, WEB-3, WEB-4, WEB-5, WEB-6, WEB-7, WEB-8, WEB-9, WEB-10, WEB-11, WEB-13
| Completed | update database doc. | 1 - High | Reviewed | 1 | 41
| Completed | Settings: django | 1 - High | Reviewed | 1 | 38 |  | Alle WEB
| Completed | AWS setup | 1 - High | Reviewed | 5 | 37 |  | None
| Completed | AWS deploy | 1 - High | Reviewed | 12 | 41 |  | None
| Completed | RAPI: Authorisation | 1 - High | Reviewed | 8 | 40 |  | WEB-13
| Completed | RAPI: log | 1 - High | Reviewed | 8 | 40 |  | WEB-13
| Completed | RAPI: facility | 1 - High | Reviewed | 8 | 40 |  | WEB-13
| Completed | cron create user | 1 - High | Reviewed | 3 | 41 |  | WEB-15
| Completed | cron clean up | 1 - High | Reviewed | 5 | 41 |  | WEB-11
| Completed | test setup | 1 - High | Reviewed | 12 | 40
| Completed | fix restAPI | 1 - High | N/A | 8 | 45
| Completed | ssl certificering | 1 - High | Reviewed | 8 | 45 |  | WEB-12
| Completed | fix url's in html and url.py's | 3 - Low | N/A | 4 | 45
| Completed | fix office cant edit admin | 3 - Med | N/A | 2 | 45
| Completed | cleanup git repositorie | 2 - Med | N/A | 2 | 45
| Completed | fix tid på "personal info access" | 2 - Med | N/A | 1 | 45
| Completed | Rest Api - fix log | 1 - High | N/A | 4 | 45
| Completed | fix office homepage angående CU kode (crasher hvis ingen CU kode eksisterer) | 2 - Med | N/A | 2 | 45
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet.
Add new items by inserting new rows above this line
NTH - Website
| Temp finished | bootstrap 4 | 3 - Low | N/A | 40 | NOT FIX
| Temp finished | database fix id iteration | 3 - Low | N/A | 1 | NOT FIX
| Temp finished | logout knap på alle siderne på hjemmesiden | 3 - Low | N/A | 1 | NOT FIX

## Roadmap Website+database
An Agile Roadmap displaying milestones and activities from Raodmap Data worksheet is in this worksheet. Title is in cell B1. Results that have the phrase "No Change" are highlighted light orange, rgb(255, 230, 210). Completed milestones or activities are highlighted light green, rgb(237,251,219). | Website+Database Roadmap
Chart headings are in cells B2, D2, F2, and H2. They read: Completed, Current, Near Term, and Future. Modify these headings to change the Target selection values in the Roadmap Data table in the Roadmap Data worksheet. Cells B3 through H20 contain the Milestones and activities for the headings in this row. Milestones and activities are created in the Roadmap Data worksheet. Do NOT modify or delete entries in this worksheet. Update the Roadmap Data table in the Roadmap Data worksheet to update content in this worksheet. This is the last instruction in this worksheet. | Completed | Current | Temp finished | Future
Filtre: personal info Reviewed
Filtre: personal fac. info Reviewed
Filtre: User logs Reviewed
Filtre: Fac. Logs Reviewed
admin bruger Reviewed
csrf token inserts on all pages Reviewed
Usertype control Reviewed
Login Reviewed
LP: Office user dahboard Reviewed
LP: Field user dashboard Reviewed
LP: Edit fac. Lp Reviewed
LP: Add/edit/remove fac. Lp Reviewed
DMP: Create user Reviewed
DMP: Edit other user Reviewed
DMP: Give fac. Access Reviewed
DMP: Remove fac. Access Reviewed
DMP: Add fac. Reviewed
DMP: Remove fac. Reviewed
DMP: Edit fac. Reviewed
BF: CU code gen. Reviewed
LPF: Edit user lp Reviewed
Template: strukturer database + implementation Reviewed
update database doc. Reviewed
Settings: django Reviewed
AWS setup Reviewed
AWS deploy Reviewed
RAPI: Authorisation Reviewed
RAPI: log Reviewed
RAPI: facility Reviewed
cron create user Reviewed
cron clean up Reviewed
test setup Reviewed
fix restAPI N/A
ssl certificering Reviewed
fix url's in html and url.py's N/A
fix office cant edit admin N/A
cleanup git repositorie N/A
fix tid på "personal info access" N/A
Rest Api - fix log N/A
fix office homepage angående CU kode (crasher hvis ingen CU kode eksisterer) N/A

## Data mobile app
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Mobil app roadmap
| Total time: | 264 | days: | 37.7143
| Time left: | 0
| Time spent: | 264 | [6 empty] | Tids estimering er umiddelbart sat højt.
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer | krav
| Completed | Analyse: Fragments | 1 - High | reviewed | 8 | 43 |  | Alle
| Completed | Analyse: Rest Api | 1 - High | reviewed | 32 | 43 |  | APP-2, APP-3, APP-4, APP-6, APP-7, APP-8
| Completed | Analyse: Bluetooth | 1 - High | reviewed | 40 | 43 |  | APP-5, APP-6
| Completed | Analyse: general struktur | 1 - High | reviewed | 8 | 43 |  | Alle
| Completed | Implementing: LoginFrag | 1 - High | reviewed | 10 | 44 |  | APP-1, APP-2, APP-3
| Completed | Implementing: ScanFrag | 1 - High | reviewed | 32 | 44 |  | APP-5
| Completed | Implementing: UnlockFrag | 1 - High | reviewed | 32 | 44 |  | APP-4, APP-5, APP-6, APP-7, APP-8
| Completed | Implementing: SuccesFrag | 1 - High | reviewed | 8 | 44 |  | APP-10
| Completed | Implementing: Logout i onDestroy | 1 - High | reviewed | 8 | 44 |  | N/A
| Completed | Analyse: Finger scan | 2 - Med | N/A | 24 | 46 | ikke indført, men beskrevet | APP-3
| Completed | Implementing: Finger scan | 2 - Med | N/A | 24 |  | ikke indført, men beskrevet | APP-3
| Completed | Research | 1 - High |  | 18 | 42 |  | None
| Completed | Research | 1 - High |  | 10 | 41 |  | None
| Completed | Research | 1 - High |  | 10 | 40 |  | None
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet.
Add new items by inserting new rows above this line

## Roadmap mobile app
An Agile Roadmap displaying milestones and activities from Raodmap Data worksheet is in this worksheet. Title is in cell B1. Results that have the phrase "No Change" are highlighted light orange, rgb(255, 230, 210). Completed milestones or activities are highlighted light green, rgb(237,251,219). | Mobile Roadmap
Chart headings are in cells B2, D2, F2, and H2. They read: Completed, Current, Near Term, and Future. Modify these headings to change the Target selection values in the Roadmap Data table in the Roadmap Data worksheet. Cells B3 through H20 contain the Milestones and activities for the headings in this row. Milestones and activities are created in the Roadmap Data worksheet. Do NOT modify or delete entries in this worksheet. Update the Roadmap Data table in the Roadmap Data worksheet to update content in this worksheet. This is the last instruction in this worksheet. | Completed | Current | Temp finished | Future
Analyse: Fragments reviewed
Analyse: Rest Api reviewed
Analyse: Bluetooth reviewed
Analyse: general struktur reviewed
Implementing: LoginFrag reviewed
Implementing: ScanFrag reviewed
Implementing: UnlockFrag reviewed
Implementing: SuccesFrag reviewed
Implementing: Logout i onDestroy reviewed
Analyse: Finger scan N/A
Implementing: Finger scan N/A
Research
Research
Research

## Data embed + lock
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Embed + lock roadmap
| Total time: | 40 | days: | 5.7143
| Time left: | 0
| Time spent: | 40
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer | krav
| Completed | Function: Bluetooth communication | 1 - High | reviewed | 8 | 41 |  | EMB-1
| Completed | Function: Verify key | 1 - High | reviewed | 2 | 41 |  | EMB-3, EMB-4
| Completed | Function: Lock controller | 1 - High | reviewed | 3 | 41 |  | EMB-2, EMB-5
| Completed | Build: Lock and embed circuit | 1 - High | reviewed | 8 | 41 |  | EMB-2, EMB-5
| Completed | Buy: Hardware and components | 1 - High | reviewed | 1 | 41 |  | None
| Completed | function: clean pairing record | 1 - High | N/A | 2 | 42 |  | N/A
| Completed | Dokument: Sikkerhed | 1 - High | reviewed | 8 | 46 |  | N/A
| Completed | Test: Integration test | 1 - High | reviewed | 8 | 46 |  | N/A
Add new items by inserting new rows into the table above this line. This is the last instruction in this worksheet. | Add new items by inserting new rows above this line

## Roadmap embed + lock
An Agile Roadmap displaying milestones and activities from Raodmap Data worksheet is in this worksheet. Title is in cell B1. Results that have the phrase "No Change" are highlighted light orange, rgb(255, 230, 210). Completed milestones or activities are highlighted light green, rgb(237,251,219). | Embed Roadmap
Chart headings are in cells B2, D2, F2, and H2. They read: Completed, Current, Near Term, and Future. Modify these headings to change the Target selection values in the Roadmap Data table in the Roadmap Data worksheet. Cells B3 through H20 contain the Milestones and activities for the headings in this row. Milestones and activities are created in the Roadmap Data worksheet. Do NOT modify or delete entries in this worksheet. Update the Roadmap Data table in the Roadmap Data worksheet to update content in this worksheet. This is the last instruction in this worksheet. | Completed | Current | Temp finished | Future
Function: Bluetooth communication reviewed
Function: Verify key reviewed
Function: Lock controller reviewed
Build: Lock and embed circuit reviewed
Buy: Hardware and components reviewed
function: clean pairing record N/A
Dokument: Sikkerhed reviewed
Test: Integration test reviewed

## Total Roadmap
Website: |  |  | timer: | 479 |  | project completion rate: | 100%
App: |  |  | dage: | 68.4286
Embed: |  |  | uger: | 6.8429
| Development | [8 empty] | Test | Report
Uge | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Timer i alt | 5 | 49 | 34 | 69 | 53 | 20 | 88 | 90 | 31 | 40 | 0 | 0 | 0 | 0
Opg. 1 | [Website] Opg: AWS setup Krav: None | [Website] Opg: admin bruger Krav: WEB-2, WEB-11 | [Website] Opg: Filtre: personal info Krav: WEB-4, WEB-8 | [Website] Opg: Filtre: User logs Krav: WEB-9, WEB-10 | [Website] Opg: update database doc. Krav: | [App] Opg: Research Krav: None | [App] Opg: Analyse: Fragments Krav: Alle | [App] Opg: Implementing: LoginFrag Krav: APP-1, APP-2, APP-3 | [Website] Opg: fix restAPI Krav: | [App] Opg: Analyse: Finger scan Krav: APP-3
Opg. 2 |  | [Website] Opg: Login Krav: WEB-3 | [Website] Opg: Filtre: personal fac. info Krav: WEB-4, WEB-8 | [Website] Opg: Filtre: Fac. Logs Krav: WEB-9, WEB-10 | [Website] Opg: AWS deploy Krav: None | [Embed] Opg: function: clean pairing record Krav: N/A | [App] Opg: Analyse: Rest Api Krav: APP-2, APP-3, APP-4, APP-6, APP-7, APP-8 | [App] Opg: Implementing: ScanFrag Krav: APP-5 | [Website] Opg: ssl certificering Krav: WEB-12 | [Embed] Opg: Dokument: Sikkerhed Krav: N/A
Opg. 3 |  | [Website] Opg: LP: Office user dahboard Krav: WEB-4 | [Website] Opg: csrf token inserts on all pages Krav: | [Website] Opg: DMP: Give fac. Access Krav: WEB-4, WEB-6, WEB-7 | [Website] Opg: cron create user Krav: WEB-15 |  | [App] Opg: Analyse: Bluetooth Krav: APP-5, APP-6 | [App] Opg: Implementing: UnlockFrag Krav: APP-4, APP-5, APP-6, APP-7, APP-8 | [Website] Opg: fix url's in html and url.py's Krav: | [Embed] Opg: Test: Integration test Krav: N/A
Opg. 4 |  | [Website] Opg: LP: Field user dashboard Krav: WEB-4 | [Website] Opg: Usertype control Krav: | [Website] Opg: DMP: Remove fac. Access Krav: WEB-4, WEB-5 | [Website] Opg: cron clean up Krav: WEB-11 |  | [App] Opg: Analyse: general struktur Krav: Alle | [App] Opg: Implementing: SuccesFrag Krav: APP-10 | [Website] Opg: fix office cant edit admin Krav:
Opg. 5 |  | [Website] Opg: LP: Edit fac. Lp Krav: WEB-17 | [Website] Opg: DMP: Create user Krav: WEB-1, WEB-3, WEB-15 | [Website] Opg: RAPI: Authorisation Krav: WEB-13 | [App] Opg: Research Krav: None |  |  | [App] Opg: Implementing: Logout i onDestroy Krav: N/A | [Website] Opg: cleanup git repositorie Krav:
Opg. 6 |  | [Website] Opg: LP: Add/edit/remove fac. Lp Krav: WEB-16, WEB-17, WEB-18 | [Website] Opg: DMP: Edit other user Krav: WEB-2, WEB-4 | [Website] Opg: RAPI: log Krav: WEB-13 | [Embed] Opg: Function: Bluetooth communication Krav: EMB-1 |  |  |  | [Website] Opg: fix tid på "personal info access" Krav:
Opg. 7 |  | [Website] Opg: Template: strukturer database + implementation Krav: WEB-1, WEB-2, WEB-3, WEB-4, WEB-5, WEB-6, WEB-7, WEB-8, WEB-9, WEB-10, WEB-11, WEB-13 | [Website] Opg: DMP: Add fac. Krav: WEB-16 | [Website] Opg: RAPI: facility Krav: WEB-13 | [Embed] Opg: Function: Verify key Krav: EMB-3, EMB-4 |  |  |  | [Website] Opg: Rest Api - fix log Krav:
Opg. 8 |  | [Website] Opg: Settings: django Krav: Alle WEB | [Website] Opg: DMP: Remove fac. Krav: WEB-18 | [Website] Opg: test setup Krav: | [Embed] Opg: Function: Lock controller Krav: EMB-2, EMB-5 |  |  |  | [Website] Opg: fix office homepage angående CU kode (crasher hvis ingen CU kode eksisterer) Krav:
Opg. 9 |  |  | [Website] Opg: DMP: Edit fac. Krav: WEB-17 | [App] Opg: Research Krav: None | [Embed] Opg: Build: Lock and embed circuit Krav: EMB-2, EMB-5
Opg. 10 |  |  | [Website] Opg: BF: CU code gen. Krav: WEB-1, WEB-15 |  | [Embed] Opg: Buy: Hardware and components Krav: None
Opg. 11 |  |  | [Website] Opg: LPF: Edit user lp Krav: WEB-2, WEB-4

## Total data
Create an Agile Roadmap by entering important milestones or activities in the Roadmap Data table in this worksheet. The title of this worksheet is in cell B1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. | Website + database roadmap
| Total time: | 503 | days: | 71.8571
| Time left: | 0
| Time spent: | 503
Table headings are in cells B2 through E2. Use heading filters to sort the table and find specific items. The Agile Roadmap works best when the table is sorted in Ascending order by Priority, followed by Milestone or Activity. Sample data is in the Roadmap Data table from cells B3 through E12. When a milestone or activity is completed, update the corresponding Result field to show the results in the Agile Roadmap worksheet. Enter "No Change" to highlight milestones with no impact. Continue to cell A13 for the next instruction. | Target | Milestone or Activity | Priority | Result | Time estimation | Deadline (Week number) | kommentarer | krav | område | LP = landing page DMP = database manupulation page BF = background functions LPF = landing page + filter
| Completed | Filtre: personal info | 1 - High | Reviewed | 5 | 39 |  | WEB-4, WEB-8 | Website
| Completed | Filtre: personal fac. info | 1 - High | Reviewed | 5 | 39 |  | WEB-4, WEB-8 | Website
| Completed | Filtre: User logs | 1 - High | Reviewed | 6 | 40 |  | WEB-9, WEB-10 | Website
| Completed | Filtre: Fac. Logs | 1 - High | Reviewed | 1 | 40 |  | WEB-9, WEB-10 | Website
| Completed | admin bruger | 1 - High | Reviewed | 10 | 38 |  | WEB-2, WEB-11 | Website
| Completed | csrf token inserts on all pages | 1 - High | Reviewed | 1 | 39 |  |  | Website
| Completed | Usertype control | 1 - High | Reviewed | 1 | 39 | only field user can access field user page etc. |  | Website
| Completed | Login | 1 - High | Reviewed | 10 | 38 |  | WEB-3 | Website
| Completed | LP: Office user dahboard | 1 - High | Reviewed | 6 | 38 |  | WEB-4 | Website
| Completed | LP: Field user dashboard | 1 - High | Reviewed | 4 | 38 |  | WEB-4 | Website
| Completed | LP: Edit fac. Lp | 1 - High | Reviewed | 4 | 38 |  | WEB-17 | Website
| Completed | LP: Add/edit/remove fac. Lp | 1 - High | Reviewed | 4 | 38 |  | WEB-16, WEB-17, WEB-18 | Website
| Completed | DMP: Create user | 1 - High | Reviewed | 2.5 | 39 |  | WEB-1, WEB-3, WEB-15 | Website
| Completed | DMP: Edit other user | 1 - High | Reviewed | 4 | 39 |  | WEB-2, WEB-4 | Website
| Completed | DMP: Give fac. Access | 1 - High | Reviewed | 8 | 40 |  | WEB-4, WEB-6, WEB-7 | Website
| Completed | DMP: Remove fac. Access | 1 - High | Reviewed | 8 | 40 |  | WEB-4, WEB-5 | Website
| Completed | DMP: Add fac. | 1 - High | Reviewed | 2.5 | 39 |  | WEB-16 | Website
| Completed | DMP: Remove fac. | 1 - High | Reviewed | 2.5 | 39 |  | WEB-18 | Website
| Completed | DMP: Edit fac. | 1 - High | Reviewed | 2.5 | 39 |  | WEB-17 | Website
| Completed | BF: CU code gen. | 1 - High | Reviewed | 4 | 39 |  | WEB-1, WEB-15 | Website
| Completed | LPF: Edit user lp | 1 - High | Reviewed | 4 | 39 |  | WEB-2, WEB-4 | Website
| Completed | Template: strukturer database + implementation | 1 - High | Reviewed | 10 | 38 |  | WEB-1, WEB-2, WEB-3, WEB-4, WEB-5, WEB-6, WEB-7, WEB-8, WEB-9, WEB-10, WEB-11, WEB-13 | Website
| Completed | update database doc. | 1 - High | Reviewed | 1 | 41 |  |  | Website
| Completed | Settings: django | 1 - High | Reviewed | 1 | 38 |  | Alle WEB | Website
| Completed | AWS setup | 1 - High | Reviewed | 5 | 37 |  | None | Website
| Completed | AWS deploy | 1 - High | Reviewed | 12 | 41 |  | None | Website
| Completed | RAPI: Authorisation | 1 - High | Reviewed | 8 | 40 |  | WEB-13 | Website
| Completed | RAPI: log | 1 - High | Reviewed | 8 | 40 |  | WEB-13 | Website
| Completed | RAPI: facility | 1 - High | Reviewed | 8 | 40 |  | WEB-13 | Website
| Completed | cron create user | 1 - High | Reviewed | 3 | 41 |  | WEB-15 | Website
| Completed | cron clean up | 1 - High | Reviewed | 5 | 41 |  | WEB-11 | Website
| Completed | test setup | 1 - High | Reviewed | 12 | 40 |  |  | Website
| Completed | fix restAPI | 1 - High | N/A | 8 | 45 |  |  | Website
| Completed | ssl certificering | 1 - High | Reviewed | 8 | 45 |  | WEB-12 | Website
| Completed | fix url's in html and url.py's | 3 - Low | N/A | 4 | 45 |  |  | Website
| Completed | fix office cant edit admin | 3 - Med | N/A | 2 | 45 |  |  | Website
| Completed | cleanup git repositorie | 2 - Med | N/A | 2 | 45 |  |  | Website
| Completed | fix tid på "personal info access" | 2 - Med | N/A | 1 | 45 |  |  | Website
| Completed | Rest Api - fix log | 1 - High | N/A | 4 | 45 |  |  | Website
| Completed | fix office homepage angående CU kode (crasher hvis ingen CU kode eksisterer) | 2 - Med | N/A | 2 | 45 |  |  | Website
| Completed | Analyse: Fragments | 1 - High | reviewed | 8 | 43 |  | Alle | App
| Completed | Analyse: Rest Api | 1 - High | reviewed | 32 | 43 |  | APP-2, APP-3, APP-4, APP-6, APP-7, APP-8 | App
| Completed | Analyse: Bluetooth | 1 - High | reviewed | 40 | 43 |  | APP-5, APP-6 | App
| Completed | Analyse: general struktur | 1 - High | reviewed | 8 | 43 |  | Alle | App
| Completed | Implementing: LoginFrag | 1 - High | reviewed | 10 | 44 |  | APP-1, APP-2, APP-3 | App
| Completed | Implementing: ScanFrag | 1 - High | reviewed | 32 | 44 |  | APP-5 | App
| Completed | Implementing: UnlockFrag | 1 - High | reviewed | 32 | 44 |  | APP-4, APP-5, APP-6, APP-7, APP-8 | App
| Completed | Implementing: SuccesFrag | 1 - High | reviewed | 8 | 44 |  | APP-10 | App
| Completed | Implementing: Logout i onDestroy | 1 - High | reviewed | 8 | 44 |  | N/A | App
| Completed | Analyse: Finger scan | 2 - Med | N/A | 24 | 46 | ikke indført, men beskrevet | APP-3 | App
| Completed | Implementing: Finger scan | 2 - Med | N/A | 24 |  | ikke indført, men beskrevet | APP-3 | App
| Completed | Research | 1 - High |  | 18 | 42 |  | None | App
| Completed | Research | 1 - High |  | 10 | 41 |  | None | App
| Completed | Research | 1 - High |  | 10 | 40 |  | None | App
| Completed | Function: Bluetooth communication | 1 - High | reviewed | 8 | 41 |  | EMB-1 | Embed
| Completed | Function: Verify key | 1 - High | reviewed | 2 | 41 |  | EMB-3, EMB-4 | Embed
| Completed | Function: Lock controller | 1 - High | reviewed | 3 | 41 |  | EMB-2, EMB-5 | Embed
| Completed | Build: Lock and embed circuit | 1 - High | reviewed | 8 | 41 |  | EMB-2, EMB-5 | Embed
| Completed | Buy: Hardware and components | 1 - High | reviewed | 1 | 41 |  | None | Embed
| Completed | function: clean pairing record | 1 - High | N/A | 2 | 42 |  | N/A | Embed
| Completed | Dokument: Sikkerhed | 1 - High | reviewed | 8 | 46 |  | N/A | Embed
| Completed | Test: Integration test | 1 - High | reviewed | 8 | 46 |  | N/A | Embed
Add new items by inserting new rows above this line
NTH - Website
| Temp finished | bootstrap 4 | 3 - Low | N/A | 40 | NOT FIX
| Temp finished | database fix id iteration | 3 - Low | N/A | 1 | NOT FIX
| Temp finished | logout knap på alle siderne på hjemmesiden | 3 - Low | N/A | 1 | NOT FIX